## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | PROJECT MANAGER
PROJECT DELIVERABLE
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
00/00/0000 | 00/00/0000 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Alex B. | 2025-01-08 | 2025-01-08 | 2 | Complete
Agree on Objectives | Frank C. | 2025-09-03 | 2025-09-07 | 5 | Complete
Detailed Requirements | Jacob S. | 09/07 | 09/12 | 6 | Complete
Hardware Requirements | Jacob S. | 09/09 | 09/11 | 3 | Overdue
Final Resource Plan | Jacob S. | 09/11 | 09/15 | 5 | In Progress
Staffing | Alex B. | 09/16 | 09/17 | 2 | In Progress
Technical Requirements | Frank C. | 09/17 | 09/21 | 5 | Not Started
DB Development | Shari W. | 09/22 | 09/24 | 3 | Not Started
API Development | Shari W. | 09/23 | 09/27 | 5 | Not Started
UI Client | Alex B. | 09/25 | 09/29 | 5 | Not Started
Testing | Kennedy K. | 09/24 | 10/02 | 9 | Not Started
Development Complete | Jacob S. | 10/02 | 10/05 | 4 | Not Started
Hardware Configuration | Alex B. | 10/05 | 10/07 | 3 | Not Started
System Testing | Kennedy K. | 10/06 | 10/09 | 4 | Not Started