## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | entity-relation-mapping-tax-compliance-ai-agent
PROJECT DELIVERABLE
SCOPE STATEMENT
START DATE | END DATE | OVERALL PROGRESS
2025-06-01 | 2025-08-13 | 25%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | DELIVERABLES | COMMENTS
Kick-off & Requirements | Stephen: scope, repo setup; Sujal: docs | 2025-06-01 | 2025-06-04 | 4 | Complete | —
ITERATION #02 | Stephen: project schedule; Sujal: pdf report | 2025-06-01 | 2025-06-09 | 9 | Complete | 1) Codebase repo; 2) PDF report; 3) Project schedule
Data Collection & Prep | Stephen: verify doc coverage, collect data sources; Sujal: preprocessing scripts | 2025-06-05 | 2025-06-14 | 10 | In Progress | —
Entity & Relation Extraction | Stephen: define taxonomy, annotate samples; Sujal: implement & train NER | 2025-06-15 | 2025-07-05 | 21 | Not Started | Partial extractor code
Knowledge Graph Build | Stephen: validate semantic accuracy; Sujal: import pipeline & QA scripts | 2025-07-06 | 2025-07-20 | 15 | Not Started | Graph instance + scripts
AI-Agent Prototype | Stephen: author sample Q&A; Sujal: build backend & frontend | 2025-07-21 | 2025-08-04 | 15 | Not Started | Agent prototype (code)
Integration & Testing | Stephen: domain QA; Sujal: debugging & tuning | 2025-08-05 | 2025-08-09 | 5 | Not Started | Tested system
Final Deliverables Prep | Stephen: report sections on tax logic; Sujal: methods & results, slides | 2025-08-10 | 2025-08-13 | 4 | Not Started | 1) Codebase repo; 2) PDF report; 3) PowerPoint deck